## Sheet1
Tasks | Owners | Pessimistic | Most Likely | Optimistic | PERT Result | Total for Subsystem
Program structure | [5 empty] | 19.3333
Comment and reorganise code | WCJ | 24 | 12 | 6 | 13
Add in event handling | WCJ | 6 | 3 | 1 | 3.1667
Add in error handling | WCJ | 6 | 3 | 1 | 3.1667
GUI subsystem | [5 empty] | 2.475
Implement base class | KH | 3 | 2 | 1 | 2
Button class | KH | 1 | 0.4 | 0.25 | 0.475
Information pane class | KH | 1 | 0.4 | 0.25 | 0.275
Input system | [5 empty] | 8.225
Verify importing works | WCJ | 12 | 6 | 2 | 6.3333
Implement gui buttons in input panel | KH | 1 | 0.4 | 0.25 | 0.475
Handle data compression + preparation | WCJ | 4 | 1 | 0.5 | 1.4167
Simulation subsystem | [5 empty] | 33.7833
Expand the filters on the view | KH | 15 | 10 | 3 | 9.6667
Implement button print simulation | KH | 25 | 20 | 10 | 19.1667
Implement button end simulation | KH | 0.4 | 0.3 | 0.1 | 0.28333
Expand data recording for output | KH | 5 | 2 | 1 | 2.3333
Package the data for the output stage | KH | 5 | 2 | 1 | 2.3333
Total
63.8167